## Timeline Information
Task # | Task Name | Duration | Start Date | End Date | Dependency | Resource
1 | Develop Timeline Wizard | 30 d | 1997-07-17 | 1997-08-15 |  | Jason
2 | Beta I |  | 1997-07-26 |  |  | Program Team
3 | Develop Layout Wizard | 16 d | 1997-07-17 | 1997-08-01 |  | Matt
4 | Beta II |  | 1997-08-11 |  |  | Program Team
5 | Develop Orgchart Wizard | 25 d | 1997-07-17 | 1997-08-10 |  | Keri
6 | Write Documentation | 2 w | 1997-08-11 | 1997-08-24 | 5 | User Ed
7 | Beta III |  | 1997-08-25 |  |  | Program Team
8 | Print Manuals | 1 w | 1997-08-25 | 1997-08-31 |  | Media Now
9 | Assemble Product | 2 d | 1997-09-01 | 1997-09-02 | 8 | Media Now
10 | Ship Visio |  | 1997-09-03 |  | 9 | Visio Corporation

## TimelineWizardData (hidden)
C:\Visio\Add-ons\Timeline.exe